## Sheet1
Week | Machine learning MS | Flask webapp creation
2022-09-19 | Build system including automated build process
2022-09-26 | test continuous delivery | Build system including automated build process
2022-10-03 | Build basic machine learning API | test continuous delivery
2022-10-10 | Research and decide machine learning model to use | connect to the machine learning API
2022-10-17 | Test and validate with dataset from kaggle | build interface for the webapp
2022-10-24 | Improvement on the machine learning model used | Improvement of the web interface together with the UX team
2022-10-31 | Improvement on the machine learning model used | setup continuous delivering and automation of deployment
2022-11-07 | Machine learning microservice ready for QA | Flask webapp ready for QA
2022-11-14 | Machine learning microservice ready for QA | Flask webapp ready for QA
2022-11-21
2022-11-28
2022-12-05
| Goals | Goals
| Build basic machine learning API | Creation of the basic webapp
| Test and validate with dataset from kaggle | Improvement of the web interface together with the UX team
Reach goal accuracy level