## Sheet1
Quarter | Week | Machine learning MS | Task difficulty | Flask webapp creation | Task difficulty
Q3 | 2022-09-19 | Build system including automated build process | 1
Q3 | 2022-09-26 | test continuous delivery | 2
Q3 | 2022-10-03 | test continuous delivery | 2
Q4 | 2022-10-10 | Build basic machine learning API | 3
Q4 | 2022-10-17 | Research and decide machine learning model to use | 2
Q4 | 2022-10-24 | Research and decide machine learning model to use | 2
Q4 | 2022-10-31 | Research and decide machine learning model to use | 2
Q4 | 2022-11-07 | Research and decide machine learning model to use | 2
Q4 | 2022-11-14 | Research and decide machine learning model to use | 2 | Build system including automated build process | 2
Q4 | 2022-11-21 | Test and validate with dataset from kaggle | 3 | test continuous delivery | 1
Q4 | 2022-11-28 | Test and validate with dataset from kaggle | 3 | test continuous delivery | 1
Q4 | 2022-12-05 | Test and validate with dataset from kaggle | 3 | connect to the machine learning API | 1
Q4 | 2022-12-12 | Improvement on the machine learning model used | 3 | connect to the machine learning API | 1
Q4 | 2022-12-19 | Improvement on the machine learning model used | 3 | connect to the machine learning API | 1
Q4 | 2022-12-26 | Improvement on the machine learning model used | 3 | build interface for the webapp | 2
Q1 | 2023-01-02 | Machine learning microservice ready for QA | 1 | Improvement of the web interface together with the UX team | 3
Q1 | 2023-01-09 | Machine learning microservice ready for QA | 1 | Improvement of the web interface together with the UX team | 3
Q1 | 2023-01-16 |  |  | Improvement of the web interface together with the UX team | 3
Q1 | 2023-01-23 |  |  | Improvement of the web interface together with the UX team | 3
Q1 | 2023-01-30 |  |  | setup continuous delivering and automation of deployment | 2
Q1 | 2023-02-06 |  |  | setup continuous delivering and automation of deployment | 2
Q1 | 2023-02-13 |  |  | setup continuous delivering and automation of deployment | 2
Q1 | 2023-02-20 |  |  | Flask webapp ready for QA | 1
Q1 | 2023-02-27 |  |  | Flask webapp ready for QA | 1
|  | Goals |  | Goals
|  | Build basic machine learning API |  | Creation of the basic webapp
|  | Test and validate with dataset from kaggle |  | Improvement of the web interface together with the UX team
Reach goal accuracy level